## 1
Please ensure this tracking sheet is completed as a group, as it will be used to monitor your individual participation within the team.
Team Members | Role/ Responsibilty | Email
Kevin Rebakure | Database Administrator and Documentation writer | r.kevin@alustudent.com
Elie Kuradusenge | Data Engineer | e.kuradusen@alustudent.com
Victor Mugisha Shyaka | Backend Developer | m.victor@alustudent.com
Deborah Kamikazi | Frontend Developer | k.deborah@alustudent.com
Task Allocation and Tracker
| Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
| Data Integration Pipeline | Elie Kuradusenge | 2026-02-15 | Completed | Yes | Requires input from Backend and Data teams.
| System Architecture Diagram | Elie Kuradusenge | 2026-02-16 | Completed | Yes | Database normalization and structure.
| Dataset Analysis & Context Explanation | Kevin Rebakure | 2026-02-17 | Completed | Yes | Focus on data sourcing and domain.
| Data Cleaning & Normalization | Kevin Rebakure and Elie Kuradusenge | 2026-02-17 | Completed | Yes | Core CRUD operations implementation.
| Database Design & Implementation | Kevin Rebakure | 2026-02-17 | Completed | Yes | Must include a minimum of 3 chart types.
| Backend API Development: | Victor Mugisha Shyaka | 2026-02-18 | Completed | Yes | Test functionality across all endpoints.
| Backend and Database Integration | Victor Mugisha Shyaka | 2026-02-18 | Completed | Yes
| Frontend Dashboard Development | Deborah Kamikazi | 2026-02-19 | Completed | Yes | Include Big O notation analysis.
| Technical Video Recording | Deborah Kamikazi | 2026-02-19 | Completed | Yes | Setup instructions for client and server.
Meeting Attendance Log
Meeting Date | Agenda | Facilitator | Attendees | Key Discussion Points | Next Steps
2025-12-13 | Finalize the DB schema and API endpoints. |  | Elie Kuradusenge
Rebakure Kevin
Victor Mugisha Shyaka
Deborah Kamikazi
2026-02-16 | Verify the ingestion of cleaned data into the DB. |  | Elie Kuradusenge
Rebakure Kevin
Victor Mugisha Shyaka
Deborah Kamikazi
2026-02-17 | Test API connectivity with Deborah’s dashboard. |  | Elie Kuradusenge
Rebakure Kevin
Victor Mugisha Shyaka
Deborah Kamikazi
2026-02-18 | Conduct end-to-end testing of the dashboard. |  | Elie Kuradusenge
Rebakure Kevin
Victor Mugisha Shyaka
Deborah Kamikazi
2026-02-19 | Record the video walkthrough and finalize the PDF. |  | Elie Kuradusenge
Rebakure Kevin
Victor Mugisha Shyaka
Deborah Kamikazi

## Sheet3
Task Allocated | Assigned Member | Deadline | Completion Status (Not Started/In Progress/Completed/Did not participate) | Reviewed by Team? (Yes/No) | Comments
Explain dataset and its context (PDF) | Elie Kuradusenge | 2026-03-01 | Not Started | No | Focus on data sourcing and domain.
Design and implement database schema | Rebakure Kevin | 2026-03-05 | Not Started | No | Database normalization and structure.
Develop Backend API endpoints | Mugisha Shyaka Victor | 2026-03-08 | Not Started | No | Core CRUD operations implementation.
Create Charts for data visualization | Kamikazi Deborah | 2026-03-10 | Not Started | No | Must include a minimum of 3 chart types.
System Architecture Diagram & Trade-offs (PDF) | Elie Kuradusenge | 2026-03-12 | Not Started | No | Requires input from Backend and Data teams.
Implement Custom Algorithm Code & Pseudo Code (PDF) | Rebakure Kevin | 2026-03-12 | Not Started | No | Include Big O notation analysis.
Implement Filtering, Sorting, Searching (Frontend) | Kamikazi Deborah | 2026-03-15 | Not Started | No | Test functionality across all data views.
Write README and Project Structure (Extra) | Mugisha Shyaka Victor | 2026-03-17 | Not Started | No | Setup instructions for client and server.
Record YouTube Video (Overview & Architecture) | Elie Kuradusenge | 2026-03-18 | Not Started | No | Script must be approved by the team.